## product_backlog
NO | USER Story | point | piority
1 | As a user,I can add and view income and expense so that I know how much money I have. | 8 | H
2 | As a user,I can edit income and expense (amount,date,category,description). | 7 | H
3 | As a user, I want to delete income and expense. | 5 | M
4 | As a user, I want to add my own categories. | 3 | L
5 | As a user, I want to see current balance, total income, and total expense. | 5 | H
6 | As a user, I want to see how much I spend for each month | 13 | H
7 | As a user, I want to see how much I spend for each category for a specific month | 8 | H
8 | As a user, I want to be able to add repeating income or expense: every day, every week, every month, so that income/expense are added automatically | 20 | M
9 | As a user, I want to see bar chart showing how much I spend each day for a specific month | 20 | L
10 | As a user, I want to see pie chart showing how much I spend for each category for a specific month | 20 | L
11
12
13
14
15
16

## sprint_backlog
sprint_backlog | NO | USER Story | point | piority
1 | 1 | As a user,I can add and view income and expense so that I know how much money I have. | 8 | H
|  | Total Point | 8
sprint_backlog | NO | USER Story | point | piority
2 | 2 | As a user,I can edit income and expense (amount,date,category,description). | 7 | H
| 3 | As a user, I want to delete income and expense. | 5 | H
| 5 | As a user, I want to see current balance, total income, and total expense. | 5 | H
|  | Total Point | 17

## burndown_chart
Sprint.No | Day | Point Planned | Point Left | User Story Done | Point of User Story Done
1 | 0 | 8 | 8 | . | 0
| 1 | 7 | 8 | . | 0
| 2 | 6 | 8 | . | 0
| 3 | 5 | 8 | . | 0
| 4 | 4 | 0 | 1 | 8
| 5 | 3 | 0 | . | 0
| 6 | 0 | 0 | . | 0
| 7 | 0 | 0 | . | 0
Sprint.No | Day | Point Planned | Point Left | User Story Done | Point of User Story Done
2 | 0 | 17 | 17 | . | 0
| 1 | 15 | 17 | . | 0
| 2 | 12 | 12 | 5 | 5
| 3 | 9 | 12 | . | 0
| 4 | 7 | 12 | . | 0
| 5 | 4 | 5 | 2 | 7
| 6 | 3 | 0 | 3 | 5
| 7 | 0 | 0 | . | 0